## Risk Conventions
Level |  | Likelihood | Severity | Severity | 5 | 5 | 10 | 15 | 20 | 25 | Risk Quantification | Consequence
5 | Maximum | 100% | Unacceptable |  | 4 | 4 | 8 | 12 | 16 | 20 | >20 | Maximum disruption of project plan. Implement new process or plan
4 | High | 10% | Major reduction in mission objectives |  | 3 | 3 | 6 | 9 | 12 | 15 | 15-20 | High disruption of project plan. Implement new project or plan
3 | Medium | 1% | Moderate reduction |  | 2 | 2 | 4 | 6 | 8 | 10 | 10-14 | Some disruption of project plan. Consider alternative process
2 | Low | 0.1% | Moderate reduction |  | 1 | 1 | 2 | 3 | 4 | 5 | 5-9 | Little disruption of project plan. Management actions
1 | Minimum | less than 0.1% | Minimal or no impact |  |  | 1 | 2 | 3 | 4 | 5 | <5 | Little to no disruption. Mitigate with management
Likelihood
Severity
5 | Maximum | Unacceptable
4 | High | Major reduction in mission objectives
3 | Medium | Moderate reduction
2 | Low | Moderate reduction
1 | Minimum | Minimal or no impact

## Project-level Risks
Code | Risk Name | S | L | SxL | Description | Mitigation Strategy
PL-1 | Regulations change | 5 | 2 | 10 | Regulations change drastically in the next 5 years | Close regulation monitoring during design.
PL-2 | Battery technology level not achieved | 4 | 3 | 12 | The energy density level of available batteries does not surpass the 400 Wh/kg | Usage of alternative energetic systems
PL-3 | In-house technology development not achieved | 3 | 3 | 9 | The required propietary technologies are not developed successfully | Usage of comercial alternatives compromising market competitiveness
PL-4 | Funding not achieved | 4 | 3 | 12 | Capital investors or funding opportunities are not interested in the project | Major project focus change to attract the capital necessary
PL-5 | Manufacturing capabilities not as efficient as estimated | 2 | 2 | 4 | The engineering and production costs grow because of manufacturing limitations | Close production engineering monitoring from early stages of the design
PL-6 | Aircraft modularity compromises the eVTOL mission | 5 | 3 | 15 | The modularity makes the project too complex and the resulting configurations are not as efficient as required | Top mission priorities definition and system-level analysis from the beginning of the project
PL-7 | Proof-of-concept not achievable | 4 | 2 | 8 | The concept results unachievable by the deadline for the PoC | Redefinition of the PoC and resource intesification towards this objective
PL-8 | Market shift in mobility trends | 3 | 1 | 3 | The air mobility is no longer a need for the market | Shifting focus to other market needs (cargo, military, etc)
PL-9 | Certification not achievable | 5 | 3 | 15 | The regulators impose higher levels for certification that make the aircraft non-viable | Major aircraft design changes need to be made

## Subsystem Risks
Code | Risk Name | S | L | SxL | Description | Mitigation Strategy
PL-1 | Regulations change | 5 | 2 | 10
15
21
5
3

## Other Risks
Code | Risk Name | S | L | SxL | Description | Mitigation Strategy
PL-1 | Regulations change | 5 | 2 | 10
15
21
5
3